## Revision History
Synechron
Automation Estimation
Version History
Date | Version | Author | Description
2012-11-23 | 0.1 | QA CoE | Initial Draft
2012-11-24 | 1 | QA CoE | Final version after review
Reviewed By
Date | Name
2012-11-24 | Venu M.S

## Test Case Prioritization
Test Case Prioritization
Manual Test Case ID | Manual Execution Efforts (Hrs) (1 and Above) | Priority | Priority Rating | Test Case Resulted in Defect | Defect Rating | Automation Complexity (Easy-5, Tough-1) | Total
Valid Login | 1 | High | 3 | Critical | 4 | 5 | 13
Invalid Login |  | Medium | 2 |  |  |  | 2
Valid Username |  | Low | 1 |  |  |  | 1
Invalid Username | [6 empty] | 0
0
0
0
0
0
0
0
0
0
Note: Please Edit Yellow color cells with actual values

## Test Case Analysis
Test Case Analysis
Test Case ID | Data Sets | Variable Data Columns | Test Data Complexity | No. Of Action Steps | No. Of Verification Steps | Automation Complexity
Valid Login | 4 | 30 | Complex | 4 | 10 | Medium
Invalid Login | 5 | 4 | Simple | 4 | 2 | Simple
Valid Username | 2 | 3 | Simple | 3 | 10 | Medium
Invalid Username | 2 | 3 | Simple | 3 | 20 | Complex
Note: Please Edit Yellow color cells with actual values

## Automation Estimation
Complexity Based Automation Estimation
S No. | Components of Test Automation Development | Complexity | Per Person Days | Description | Units | Days
1 | KT/Requirement Analysis |  |  | To understand the application and to analyze the manual test cases that have to be converted for automation |  | 1 | One Time Activity
2 | Test Automation Plan |  |  | To create the Automation Test Plan |  | 2
3 | Test Case Analysis | Simple | 30 | Refer to Test Case Analysis Sheet | 100 | 3.3333
|  | Medium | 20 |  | 100 | 5
|  | Complex | 10 |  | 100 | 10
4 | Framework Design
| Generic Function identification and development, creating folder structure etc. |  | 3 |  |  | 3
| Application specific functions Identification |  | 3 |  |  | 3
| Framework Implementation |  | 3 |  |  | 3
| Documentation such as framework, guidelines |  | 3 |  |  | 3
5 | Automation Development | [5 empty] | Per Script Activities
| Activities: 1. Object Repository creation 2. Script Development 3. Integration / Execution | Simple | 1 | Refer to Test Case Analysis Sheet | 100 | 100
|  | Medium | 0.5 |  | 100 | 200
|  | Complex | 0.25 |  | 100 | 400
6 | Test Data Development
| Activities: 1. Test data creation | Simple | 3 | Refer to Test Case Analysis Sheet | 100 | 33.3333
|  | Medium | 2 |  | 100 | 50
|  | Complex | 1 |  | 100 | 100
7 | Test Case Review Activities: 1. Peer Review 2. Unit Testing |  |  | We consider 10 percent of total time required for Automation development and Test data development for review and unit testing. |  | 88.3333
|  |  |  | Total Number of Person Days |  | 1005
|  |  |  | Total number of person days (considering 10 % Buffer) |  | 1015.05
Note: Please Edit Yellow color cells with actual values