## Revision History
Synechron
Complexity Based Estimation
Version History
Date | Version | Author | Description
2012-11-23 | 0.1 | QA CoE | Initial Draft
2012-11-24 | 1 | QA CoE | Final version after review
Reviewed By
Date | Name
2012-11-24 | Venu M.S

## Complexity Estimation
Complexity Estimation
|  | Total Estimated (Hrs.) | 45.3333
|  | For Review and update (Hrs.) | 9.0667
|  | For Reporting (Hrs.) | 4.5333
|  | For Communication (Hrs.) | 6.8
|  | Total (Hrs.) | 65.7333
|  | Total Man Days. | 8.2167
|  | No. of Resources | 3
|  | Days / Resource | 2.7389
Type&Complexity | Sr. No. | Module Name | Sub Module Name | Type | Nos. of Functional Conditions | No. of UI Components | Complexity | Estimated Hrs. / Component | Total Hrs. | Total Man Days
Functional4-Complex | 1 |  |  | Functional | 5 |  | 4-Complex | 4 | 20 | 2.5 | UI1-Low | 0.16667
Functional2-Medium | 2 |  |  | Functional | 8 |  | 2-Medium | 1 | 8 | 1 | UI2-Medium | 0.25
Functional3-High | 3 |  |  | Functional | 2 | 6 | 3-High | 2 | 16 | 2 | UI3-High | 0.33333
UI3-High | 4 |  |  | UI |  | 4 | 3-High | 0.33333 | 1.3333 | 0.16667 | UI4-Complex | 0.5
| 5 | [6 empty] | 0 | 0 | 0 | Functional1-Low | 0.5
| 6 | [6 empty] | 0 | 0 | 0 | Functional2-Medium | 1
| 7 | [6 empty] | 0 | 0 | 0 | Functional3-High | 2
| 8 | [6 empty] | 0 | 0 | 0 | Functional4-Complex | 4

## Guidelines
Guidelines
Guidelines/Instructions:
Module Name: This column is used to define module name of the application for which user has to estimate. Sub Module Name: This column is used to define sub module name of the application for which user has to estimate. Type: This column is used to define the type of entered module (For eg. UI Testing, Functional Testing, Integration Testing, etc.) No. of Functional Conditions: This column depicts the number of functional conditions. This column would be applicable only when the type is “Functional” and should be left empty when the type is “UI”. No. of UI Components: This column depicts the number of UI components. This column would be applicable only when the type is “UI” and should be left empty when the type is “Functional”. Complexity: This column is used to define the complexity of the module. The categories for complexity are “1-Low”, “2-Medium”, “3-High”, and “4-Complex”. Estimated Hrs.: This column will be populated automatically as per selected Type and Complexity. Total Hrs.: This will be calculated automatically and the value is (Nos. of functional condition or Nos. Of UI Components) x Estimated Hrs. Total Man Days: This will be calculated automatically and the value is Totals No. of Hrs. / 8